## PEMPAL TCoP Action Plan for FY 2016

PEMPAL Treasury CoP Action Plan for FY2016 presents a continuation of TCOP action plan for FY2013-15 which was developed in line with the main objectives and activities envisaged in PEMPAL Strategy for 2012-2017.

The main mid-term objectives of the Treasury CoP following from the PEMPAL Strategy are:

1.  Supporting and enabling promotion of PFM reforms in PEMPAL member countries, focusing on reforms of national treasuries' activities.

2. Offering good quality resources and knowledge services by topics of priority professional interest to Treasury CoP members.

3. Building and enhancing a highly professional community of treasury experts interested in promoting treasury reforms in the context of a wider PFM reform, as part of the general PEMPAL network, in Central Europe and Central Asia.

4. Involving top managers of Treasuries and MoFs from member countries to support the TCoP activities and PEMPAL network in general.

During the period 2013-2015 the TCoP organized its activities around the following four main themes:

1. Use of information technologies in treasury operations;

2. Accounting and financial reporting in public sector;

3. Cash management

4. Treasury control

The CoP made good progress in exploring various issues under these themes over the last three years, and activities envisaged for FY16 are expected to build on that progress. In particular, several thematic groups have been launched within the CoP and are expected to deliver important intermediate results in FY16. The main themes of TCOP activities therefore continue to be the same.

Information on TCoP activities, objectives, target audience, tentative locations and estimated budget of the events envisaged by the Plan is presented in Annex A. The tentative calendar plan of events is presented in Annex B.  In line with the current COP practice, TCoP Executive Committee will be confirming the event topics and content of agendas closer to the dates of the events, in consultations with the COP members.

The following formats of events preferred by the TCoP members are included in the Plan:

- Small group workshops with participants from 5-6 countries maximum

- Thematic video conferences

- TCOP plenary meeting

- TCOP Executive Committee meetings

TCoP Executive Committee will continue to organize and coordinate the TCoP activities. It will hold its meetings via video-conferences or face-to-face.

The total TCoP Budget for FY 2016 is USD 330 thousand.

Annex  А

TCOP Action Plan FY2016.

| Activity | Type and description of activity | Target participants | Place and duration | Preliminary budget |
| --- | --- | --- | --- | --- |
| Objective 1: Supporting and enabling promotion of PFM reforms in PEMPAL member countries, focusing on reforms of national treasuries' activities |
| TCoP PFM priority theme: 1.1 “Use of Information technologies in Treasury operations” | 1 Small-format workshop Sharing lessons learnt through FMIS implementation (based on experience of one of the member countries, tentatively - Tajikistan) 2 thematic video-conferences Sharing experience on various aspects of FMIS implementation | Members of the thematic group on use of IT in treasury operation (about 20 participants) Maximum 10 video-communication spots (about 20 participants) | Tentative location – Dushanbe, Tajikistan Duration - 3 days Duration - 3 hours | USD 50.000 USD 500 (per event) |
| TCoP PFM priority theme: 1.2 “Accounting and financial reporting in public sector” | 1 Small format workshop Discussions on essential elements of the plan for reforming the public sector accounting system. Providing peer assistance to one of the member countries (tentatively – Belarus) | Members of the thematic group on Accounting Standards (about 20 participants) | Tentative location – Minsk, Belarus Duration - 3 days | USD 50.000 |
| TCoP PFM priority theme: 1.3 “Cash management” | 1 TCoP Plenary Discussing and sharing experience on the issues under the topic identified by the members 1 Small-format workshop on cash management Addressing the issues related to the topic envisaged in the thematic group Action Plan 1 thematic video-conference Discussing and sharing experience on the issues of priority interest under the topic | TCoP members (about 50 participants) Members of the thematic group on Cash management (about 25 participants) Maximum 10 video-communication spots (about 25 participants) | Location to be identified Duration - 3 days Location to be identified Duration - 3 days Duration - 3 hours | USD 176.000 USD 50.000 USD 500 |
| TCoP PFM priority theme: 1.4 “Treasury control” | 1 thematic video-conference Discussing and sharing experience on the issues of priority interest under the topic | Maximum 10 video-communication spots (about 25 participants) | Duration - 3 hours | USD 500 |
| Objective 2: Offering good quality resources and knowledge services by topics of priority professional interest to Treasury CoP members |
| 2.1 Use/ contribution to common PEMPAL network resources. | Further additions to PEMPAL library Uploading various materials originated from the TCoP events into the PEMPAL library | TCoP members, TCoP Resource Team | On regular basis |  |
| 2.2 Involvement of international experts | Inviting international PFM experts to participate in preparation and implementation of TCoP events and surveys Various inputs (presentations, questionnaires, comments to the prepared papers, etc) by PFM experts contracted to work with the TCoP | International PFM experts contracted to work with PEMPAL TCoP | On the TCoP Executive Committee request |  |
| Objective 3: Building and enhancing a highly professional community of treasury experts interested in promoting treasury reforms in the context of a wider PFM reform, as part of the general PEMPAL network, in Central Europe and Central Asia |
| 3.1 Assessment of the level of effectiveness and usefulness of the participation of TCoP members in COP activities | Conducting regular surveys among TCoP members in order to evaluate the successful and less successful aspects of COP activities | TCOP Executive Committee, TCoP resource team | Following each event conducted within TCoP |  |
| 3.2 TCoP Executive Committee activities | Executive Committee meetings (4 videoconferences and 1 face-to-face meeting are envisaged for this period) Discussions on the TCoP current activities and preparation of future events | Executive Committee members |  | USD 500 (per VC) |
| 3.3 Joint activities of PEMPAL CoPs | Joint meeting of PEMPAL COPs Leadership Discussions on the results of the PEMPAL midterm review. Preparation of TCOP activities for FY 2016 | Members of all TCoP Executive Committee (9 TCoP participants) | Tentative location - Slovenja Duration - 3 days | Will be financed from the PEMPAL general budget |
| 3.4 Participation in activities of the PEMPAL Steering Committee | Steering Committee meetings | TCoP Chair and deputies | Subject to decision of the Steering Committee |  |
| Objective 4: Involving top managers of Treasuries and MoFs from member countries to support the TCoP activities and PEMPAL network in general |
| 4.1 Increasing the level of awareness of the top managers of MOFs and Treasuries from member countries about the results of TCoP activity | Development and circulation of various informative materials about TCoP activities to the MOFs and Treasuries top managers | Executive Committee supported by TCoP resource group | Once a year |  |

Draft calendar plan of TCoP events  for FY2016                           Annex B

| # | Event | Planned time |
| --- | --- | --- |
|  | Events for July 2015- June 2016 |  |
| 1 | Meeting of the TCoP Executive Committee | July 2015 |
| 2 | Small format workshop on IT use in Treasury operations | September 2015 |
| 3 | Meeting of the TCoP Executive Committee (videoconference) | September 2015 |
| 4 | Thematic videoconference on cash management | October 2015 |
| 5 | Meeting in a small group on accounting and reporting in public sector | November 2015 |
| 6 | Meeting of the TCoP Executive Committee (videoconference) | November 2015 |
| 7 | Thematic videoconference on IT use in Treasury operations | December 2015 |
| 8 | Small format meeting on cash management | February 2016 |
| 9 | Meeting of the TCoP Executive Committee (videoconference) | February 2016 |
| 10 | Thematic videoconference on treasury control | March 2016 |
| 11 | Plenary workshop | May 2016 |
| 12 | Thematic videoconference on IT use in Treasury operations | June 2016 |
| 13 | Meeting of the TCoP Executive Committee (videoconference) | June 2016 |

# Footnotes

For the period July 2015-June 2016

Subject to needs of small-scale thematic groups, the number of video-conferences can be increased

The final decision on the event topics will be taken by the TCoP Executive Committee. Issues related to other TCoP priority themes might be addressed during the event

Combined with the joint meeting of PEMPAL COPs leadership in Slovenja, in July 2015