## Slide 1
  GROUP 1 - OUTPUT OBJECTIVES 1 and 2 (ENGLISH/BCS group)

## Slide 2
Question 1
Output Objective 1, PFM priorities of member governments are addressed by the PFM platform – good progress – will be achieved by end of strategy, on ongoing basis.
  But need to mitigate identified risk under this Output Objective 1, assessed as ‘moderate’ in Attachment 2 MTR Report – Ministers continue to assign participants to attend PEMPAL – may be negatively impacted depending on financial contribution strategies (connected to Objective 4 ).
  Consultation by COPs ensures priorities of members are addressed – however need to continue to ensure differentiated services are provided to ensure countries in minority still get their needs met. Continue use and exploration of different formats (working groups/study visits/peer review).
Cross-COP initiatives/projects need to be identified at earlier stages of action plan development (not after). Need to coordinate better. Need in Exec Comm meetings to look at action plans of other COPs and see if members interested in attending (to be done in a more systematic way).
  Moscow approach to identifying common projects good but need to follow through

## Slide 3
Question 1
Output Objective 2 (quality network services and products) shows good progress and will be achieved by end of strategy.
Need to continue to manage two identified existing ‘moderate’ risks –
  cost effective and sustainable communication technologies – need to keep finding and maintaining effective tools to communicate (eg webex and webinar technologies, information storage and exchange tools). Some Ministry policies disallow tools (eg skype not allowed at work) – need to manage this impact.
  visa processes sometimes prevents attendance so need to ensure event preparation continues well in advance as is current practice.
Need to manage new risks – in context of new Secretariat mechanism – capturing all data over next six months and extra support for meeting reporting obligations

## Slide 4
Question 2
Our Group examined Table 1 and provide the following priority rankings.

## Slide 5
Question 2/ Sažetak diskusije za pitanje
Output Objective 1 |  | PRIORITY
4.COP action plans could be more comprehensively presented to the SC for approval, as recommended by donors. AGREE: COPS WILL DOCUMENT PROCESS AND BACKGROUND OF HOW PRIORITIES ARE IDENTIFIED AND MET, AND PROBLEMS/ISSUES ETC AGREE: ACTION PLANS WILL INCLUDE ENVISAGED CROSS-COP ACTIVITIES, PROJECTS AND EXCHANGES (COMBINE ACTION 6 INTO THIS ACTION) | COP Chairs Deputy Chairs | To be adopted for FY17 plans in 2016. Updates on progress of implementation of FY16 to include more comprehensive presentation of results achieved, issues addressed, and work produced. HIGH
5.SC meetings could be used more effectively for cross-COP exchanges, with COPs playing a more active role (through providing more informative reports as recommended by the Ministry of Finance of the Russian Federation). AGREE: ADD REGULAR CROSS-COP AGENDA ITEM | COP ExCom | From October 2015 SC meeting HIGH

## Slide 6
Question 2/ Sažetak diskusije za pitanje
Output Objective 1 |  | PRIORITY
6.COPs could follow through with concrete actions on cross-COP exchanges identified at the Moscow 2014 meeting (as recommended by SECO). DELETE THIS AND COMBINE INTO ACTION 4 (INSERT PROJECTS IN ACTION PLANS) | COP ExCom RTs | In October 2015 SC meeting, COPs to report on progress and feasibility of any identified exchanges
7. Strengthen recording and reporting of some types of cross-COP exchanges.(ie COP members attending events of other COPs) AGREE: SUGGEST IN POST-EVENT ELECTRONIC SURVEYS, ADDITIONAL CATEOGRY OF ‘OTHER COP MEMBER – SPECIFY COP’ BE ADDED SO DATA AUTOMATICALLY COLLECTED | RTs Secretariat | Data collection to occur for all future COP meetings and to be included in quarterly reports. HIGH – IMMEDIATELY IMPLEMENTED FOR ALL FUTURE EVENTS

## Slide 7
OUTPUT OBJECTIVE 2 |  | PRIORITY
8.Confirm that benchmarking of Secretariat services, as required under Action 4, is no longer appropriate given urgency of establishing new Secretariat mechanism. ACCEPTED | PEMPAL Executive | July 2015 meeting AGREE (BUT IS IT NECESSARY TO HAVE A NEW UPDATED VERSION OF STRATEGY MID WAY THROUGH?
9.Confirm that targets indicated under Action 4 (related to delivery of the contract with the former Secretariat) can be removed from the strategy given they have been completed. ACCEPTED | PEMPAL Executive | July 2015 meeting AGREE – BUT SEE ABOVE
10.Identify and clarify the types of products and services being delivered by PEMPAL (ie more systematic approach to branding PEMPAL knowledge products and services, drawing on experiences of other networks eg CABRI) ACCEPTED | COP ExCom RTs | To be considered as part of next strategy MEDIUM/LOW BUT NEEDS TO BE ADDRESSED FOR NEXT STRATEGY (INC FEASBILITY OF COPYRIGHT OR ‘APPROVAL NEEDED FOR USE’ CLEARLY LABELED ON RELEVANT PRODUCTS)
11. Improve the collection of information about the use of PEMPAL provided or produced knowledge products (including the library once the new platform is finalized). | Secretariat RTs COPs | MEDIUM/LOW – CONNECTED TO SUGGESTION 10 ABOVE – NEEDS TO BE ADDRESSED AS PART OF NEXT STRATEGY

## Slide 8
OUTPUT OBJECTIVE 2 |  | PRIORITY
12. Ensure the quality of knowledge products and resources is maintained through regular updating where feasible. AGREE | COP ExCom RTs Secretariat | Ongoing HIGH
13.Ensure adequate resources are allocated to the effective monitoring and maintenance of website, wikis and other storage and communication repositories used by PEMPAL. AGREE | Secretariat COP ExCom RTs | To be incorporated into TOR of new Secretariat mechanism. MEDIUM – GIVEN CURRENT RESOURCING CONSTRAINTS AND NEW SECRETARIAT MECHANSIM
14.Periodically assess developing technology solutions for their applicability and usefulness in improving communication, particularly translation tools given the multi-lingual nature of the network. AGREE | Secretariat | To be incorporated into TOR of new Secretariat mechanism. MEDIUM – GIVEN CURRENT RESOURCING CONSTRAINTS AND NEW SECRETARIAT MECHANSIM
15.Clarify the role of observers and strengthen the role of COPs on the Steering Committee in line with recommendations made by donors. 16. Revist procedural to identify any changes required as a result of donor recommendations. AGREE | SC Secretariat | October 2015/January 2016 SC meeting HIGH

## Slide 9
Thank you