# AUDIT ENGAGEMENT PROGRAM

# Numărul de referinţă al documentului de lucru: A 6

| Audit engagement: Assessing the processes of coordination, monitoring, planning, execution, and reporting on expenditures made by central government authorities |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration of audit: February 20, 2017 – March 31, 2017 |  |  |  |  |  |  |  |  |
| Audit team leader – Alexandru Lungu Audit team member 1 – Maxim Bukatar Audit team member 2 – Ion Morar |  |  |  |  |  |  |  |  |
| Steps | Activity | Dates from / to | Responsibility |  |  | No. of days planned by type of activity | No. of hours planned by activity |  |
|  |  |  | Audit team leader | Audit team member 1 | Audit team member 2 |  |  |  |
| Audit planning | Audit planning. Data collection and analysis | 20-21.02.2017 | 1,75 | 2 | 2 | 5,75 | 46 |  |
|  | Organing and holding a kick-off meeting | 22.02.2017 | 0,25 | 0,25 | 0,25 | 0,75 | 6 |  |
|  | Developing a work program | 21.02.2017 | 0,25 | - | - | 0,25 | 2 |  |
| Fieldwork | Analysis of control | 22-23.02.2017 | 1,75 | 1,75 | 1,75 | 5,25 | 42 |  |
|  | Risk assessment | 24.02.2017 | 1 | 1 | 1 | 3 | 24 |  |
|  | Testing | 27.02.2017 22.03.2017 | 17 | 17 | 17 | 51 | 408 |  |
|  | Formulating audit findings and recommendations | 23.03.2017 24.03.2017 | 1,75 | 1,75 | 1,75 | 5,25 | 42 |  |
|  | Holding a meeting to complete fieldwork | 24.03.2017 | 0,25 | 0,25 | 0,25 | 0,75 | 6 |  |

| Audit report | Preparing a draft audit report | 27-28.03.2017 | 2 | 2 | 2 | 6 | 48 |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Holding a closing meeting on audit engagement | 30.03.2017 | 0,25 | 0,25 | 0,25 | 5,25 | 42 |
|  | Preparing a final audit report | 30-31.03.2017 | 1,75 | --- | --- | 1,75 | 14 |
| Total |  |  |  |  |  | 85 days | 680 hours |

Written by: Lungu Alexandru _________    Date: 21.02.2017

Led by: Livia Jandîc  _________________    Date: 21.02.2017